## NIC_NADRS
NIC - NADRS Training Plan (Updated on 08-Mar-2011)
Region | S. No. |  | State/UT | # of Employees | No Of Locations | Training Location | # of Participants | Batch size | # of Batches | 2011-02-28 |  |  | 2011-03-01 |  |  | 2011-03-02 |  |  | 2011-03-03 |  |  | 2011-03-04 |  |  | 2011-03-05 |  |  | 2011-03-06 |  |  | 2011-03-07 |  |  | 2011-03-08 |  |  | 2011-03-09 |  |  | 2011-03-10 |  |  | 2011-03-11 |  |  | 2011-03-12 |  |  | 2011-03-13 |  |  | 2011-03-14 |  |  | 2011-03-15 |  |  |  | Total
[10 empty] | Plan | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | Sun | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | Plan | Planned Attendance | Status/ Attendance | 2011-03-09 | Planned Attendance | Status/ Attendance | 2011-03-10 | Planned Attendance | Status/ Attendance | 2011-03-11 | Planned Attendance | Status/ Attendance | 2011-03-12 | Planned Attendance | Status/ Attendance | Sun | Planned Attendance | Status/ Attendance | 2011-03-14 | Planned Attendance | Status/ Attendance | 2011-03-15 | Planned Attendance | Status/ Attendance |  | Planned Attendance | Status/ Attendance
North | 1 | 1 | Bihar | 614 | 3 | Muzaffarpur | 154 | 31 | 5 |  | 31 | postponed to 3rd Mar | [6 empty] | 2011-03-03 | 31 | 29 | 2011-03-04 | 31 | 31 | 2011-03-05 | 31 | 19 |  |  |  | 2011-03-07 | 31 | 24 | 2011-03-08 | 31 | 20 | 2011-03-09 | 31 | 20 | 2011-03-10 |  | No training. Participant busy on Govt. duty | 2011-03-11 | No training | No training | 2011-03-12 | No training |  |  |  |  | Cancelled | [6 empty] | 217 | 143
[6 empty] | Patna-1 | 141 | 28 | 5 |  | 28 | postponed to 3rd Mar | [6 empty] | 2011-03-03 | 28 | 15 | 2011-03-04 | 28 | 20 | 2011-03-05 | 28 | 17 |  |  |  | 2011-03-07 | 28 | 35 | 2011-03-08 | 28 | 19 | 2011-03-09 |  | 20 | 2011-03-10 |  | 6 | 2011-03-11 | 28 | 7 | 2011-03-12 | No training |  |  |  |  | Cancelled | [6 empty] | 196 | 139
[6 empty] | Patna-2 | 140 | 28 | 5 | [9 empty] | 2011-03-03 | 28 | 15 | 2011-03-04 | 28 | 19 | 2011-03-05 | 28 | 17 |  |  |  | 2011-03-07 |  |  | 2011-03-08 |  |  | 2011-03-09 |  |  | 2011-03-10 |  |  | 2011-03-11 |  |  | 2011-03-12 | No training |  |  |  |  | Cancelled | [6 empty] | 84 | 51
[6 empty] | Bhagalpur | 177 | 36 | 5 |  | 36 | postponed to 3rd Mar | [6 empty] | 2011-03-03 | 36 | 36 | 2011-03-04 | 36 | 42 | 2011-03-05 | 36 | 33 |  |  |  | 2011-03-07 | 36 | 42 | 2011-03-08 | 36 | 16 | 2011-03-09 |  | No training. Participant busy on Govt. duty | 2011-03-10 |  | No training | 2011-03-11 |  | No training | 2011-03-12 | No training |  |  |  |  | Cancelled | [6 empty] | 216 | 169
| 2 | 2 | Chandigarh(UT) | 3 |  | Ambala | [52 empty] | 0 | 0
| 3 | 3 | Delhi (UT) | 31 | 1 | Delhi | 31 | 15 | 2 | [21 empty] | 2011-03-07 |  |  | 2011-03-08 | 15 | 14 | 2011-03-09 |  | 14 | 2011-03-10 |  | 17 |  | 17 | 17 | Finished | Finished | [11 empty] | 32 | 62
| 4 | 4 | Haryana | 159 | 3 | Ambala | 67 | 15 | 4 |  | 15 | Cancelled |  | 15 | Cancelled |  |  | Cancelled | 2011-03-03 | 15 | 10 | 2011-03-04 | 15 | 11 | [6 empty] | 2011-03-07 | 20 | 21 | 2011-03-08 | 20 | 22 | 2011-03-09 |  | 8 | 2011-03-10 |  |  | 2011-03-11 |  | No training | 2011-03-12 | Finished | [11 empty] | 100 | 72
[6 empty] | Gurgaon | 30 | 15 | 2 |  | 15 | Cancelled |  | 15 | Cancelled |  |  | Cancelled | 2011-03-03 | 15 | 7 | 2011-03-04 | 15 | 7 | [6 empty] | 2011-03-07 |  | No Training | 2011-03-08 |  | No Training | 2011-03-09 |  | No Training | 2011-03-10 |  | No Training |  |  | No training | [6 empty] | 2011-03-14 | 15 | 19 |  |  |  |  | 75 | 33
[6 empty] | Hisar | 65 | 15 | 4 |  | 15 | Cancelled |  | 15 | Cancelled |  |  | Cancelled | 2011-03-03 | 15 | 11 | 2011-03-04 | 15 | 12 | 2011-03-05 | [5 empty] | 2011-03-07 | 15 | 7 | 2011-03-08 | 15 | 25 | 2011-03-09 |  | 25 | 2011-03-10 |  |  | 2011-03-11 |  | Finished | [13 empty] | 90 | 80
|  |  | Himachal Pradesh | 77 | 3 | Dharamshala | 22 | 22 | 1 | [49 empty] | 0 | 0
| 5 | 5 |  |  |  | Solan | 40 | 20 | 2 | [26 empty] | Not started |  |  | Not Started | [19 empty] | 0 | 0
[6 empty] | Shimla | 35 | 20 | 2 | [26 empty] | Not started |  |  | Not Started | [19 empty] | 0 | 0
| 6 | 6 | Jammu & Kashmir | 176 | 3 | Jammu | 46 | 15 | 3 |  |  | 0 | [5 empty] | Cancelled | 2011-03-03 | 15 | 15 | 2011-03-04 | 15 | 10 | [6 empty] | 2011-03-07 | 20 | 9 | 2011-03-08 | 20 | 12 | 2011-03-09 |  | 12 | 2011-03-10 |  | 12 | Finished | [15 empty] | 70 | 70
[6 empty] | Srinagar-1 | 94 | 20 | 5 |  |  | 0 | [5 empty] | Cancelled | 2011-03-03 | 20 | 15 | 2011-03-04 | 20 | 15 | [6 empty] | 2011-03-07 | 20 | 14 | 2011-03-08 | 20 | 15 | 2011-03-09 |  | 15 | 2011-03-10 |  | 17 | 2011-03-11 |  | 16 | 2011-03-12 | 20 | 16 | [10 empty] | 100 | 123
[6 empty] | Srinagar-2 | [13 empty] | 12 | 15 |  | 20 | 15 | [6 empty] | 2011-03-07 |  |  | 2011-03-08 | [24 empty] | 32 | 30
[6 empty] | Udhampur | 23 | 12 | 2 |  |  | 0 | [5 empty] | Cancelled | 2011-03-03 |  |  | 2011-03-04 | 12 | 8 | [6 empty] | 2011-03-07 | 12 | 5 | 2011-03-08 | 12 | 5 | 2011-03-09 |  | 7 |  |  | 7 | Finished | [15 empty] | 36 | 32
| 7 | 7 | Punjab | 185 | 3 | Amritsar | 57 | 20 | 3 | 2011-02-28 | 20 | 18 | 2011-03-01 | 20 | 18 |  |  |  | 2011-03-03 | 20 | 17 | 2011-03-04 | 20 | 17 | [6 empty] | 2011-03-07 | 20 | 21 | 2011-03-08 | 20 | [7 empty] | Finished | [15 empty] | 120 | 91
[6 empty] | Jalandhar | 52 | 20 | 3 | 2011-02-28 | 20 | 18 | 2011-03-01 | 20 | 18 |  |  |  | 2011-03-03 | 20 | 28 | 2011-03-04 | 20 | 31 | [6 empty] | 2011-03-07 |  |  | 2011-03-08 | [8 empty] | Finished | [15 empty] | 80 | 95
[6 empty] | Patiala | 72 | 20 | 5 | 2011-02-28 | 20 | 12 | 2011-03-01 | 20 | 12 |  |  |  | 2011-03-03 | 20 | 17 | 2011-03-04 | 20 | 14 | [6 empty] | 2011-03-07 | 20 | 12 | 2011-03-08 | 20 | 24 | 2011-03-09 |  | 14 | 2011-03-10 |  | 14 | 2011-03-11 |  | 12 | 2011-03-12 |  | 12 | [10 empty] | 120 | 143
| 8 | 8 | Uttar Pradesh | 964 | 12 | Agra-1 | 77 | 15 | 5 | 2011-02-28 | 15 | 3 | 2011-03-01 | 15 | 5 | 2011-03-02 | 15 | 5 | 2011-03-03 | 15 | 3 | 2011-03-04 | 15 | 6 | 2011-03-05 | 15 | 6 |  |  |  | 2011-03-07 | 20 | 16 | 2011-03-08 | 20 | 16 | 2011-03-09 |  | 17 | 2011-03-10 |  | 17 | 2011-03-11 |  | 28 | 2011-03-12 |  | 28 | [10 empty] | 130 | 150
[6 empty] | Agra-2 | 15 | 15 | 1 | 2011-02-28 |  | 0 | 2011-03-01 | [45 empty] | 0 | 0
[6 empty] | Allahabad-1 | 95 | 20 | 5 |  | 20 | Cancelled | [6 empty] | 2011-03-03 | 20 | 15 | 2011-03-04 | 20 | 15 | [6 empty] | 2011-03-07 | 20 | 18 | 2011-03-08 | 20 | 19 | 2011-03-09 |  | 10 | [6 empty] | 2011-03-12 |  | 12 | [10 empty] | 100 | 89
[6 empty] | Allahabad-2 | [13 empty] | 20 | [10 empty] | 2011-03-07 |  |  | 2011-03-08 | [7 empty] | 10 | 2011-03-11 |  | 17 | [13 empty] | 20 | 27
[6 empty] | Bareilly | 95 | 20 | 5 | 2011-02-28 | 20 | 25 | 2011-03-01 | 20 | 25 |  |  |  | 2011-03-03 | 20 | 18 | 2011-03-04 | 20 | 18 | [6 empty] | 2011-03-07 | 20 | 15 | 2011-03-08 | 20 | 15 | 2011-03-09 |  | 16 | 2011-03-10 |  | 16 | 2011-03-11 |  | 19 | 2011-03-12 |  | 19 | [10 empty] | 120 | 186
[6 empty] | Deoria | 45 | 15 | 3 |  | 15 | Cancelled | [6 empty] | 2011-03-03 | 25 | 11 | 2011-03-04 | 25 | 11 | [6 empty] | 2011-03-07 | 15 | 13 | 2011-03-08 | 15 | 13 | [9 empty] | 2011-03-12 |  | 8 | 2011-03-13 |  | 8 | [7 empty] | 95 | 64
[6 empty] | Gorakhpur | 102 | 20 | 5 | 2011-02-28 | 40 | 16 | 2011-03-01 | 40 | 20 |  |  |  | 2011-03-03 | 20 | 16 | 2011-03-04 | 20 | 15 | [6 empty] | 2011-03-07 | 20 | 14 | 2011-03-08 | 20 | 12 | 2011-03-09 |  | 12 | 2011-03-10 |  | 7 | 2011-03-11 |  | 16 | 2011-03-12 |  | 17 | [10 empty] | 160 | 145
[6 empty] | Jhansi | 42 | 15 | 3 | 2011-02-28 | 15 | 5 | 2011-03-01 | 15 | 5 | 2011-03-02 | 15 | 4 | 2011-03-03 | 15 | 20 | 2011-03-04 | 15 | 10 | 2011-03-05 | 15 | 6 |  |  |  | 2011-03-07 | 15 | 5 | 2011-03-08 | 15 | 13 | [6 empty] | Finished | [15 empty] | 120 | 68
[6 empty] | Kanpur | 101 | 20 | 5 | 2011-02-28 | 20 | 18 | 2011-03-01 | 20 | 4 | 2011-03-02 | 20 | 7 | 2011-03-03 | 20 | 7 | 2011-03-04 | 20 | 7 | 2011-03-05 | [5 empty] | 2011-03-07 | 20 | 16 | 2011-03-08 | 20 | 11 | 2011-03-09 |  | 20 | 2011-03-10 |  | 5 | 2011-03-11 | 20 | 11 | 2011-03-12 | 20 | 7 | [10 empty] | 180 | 113
[6 empty] | Lucknow 1 | 92 | 18 | 5 | 2011-02-28 | 18 | 7 | 2011-03-01 | 18 | 5 |  |  | 15 | 2011-03-03 | 18 | 15 | 2011-03-04 | 18 | 7 |  | 18 | 8 |  |  |  | 2011-03-07 | 18 | 17 | 2011-03-08 | 18 | 22 | 2011-03-09 |  | 16 | 2011-03-10 |  | 13 | 2011-03-11 |  | 20 | 2011-03-12 |  | 11 | [10 empty] | 126 | 156
[6 empty] | Lucknow -2 | 80 | 20 | 4 | 2011-02-28 | 20 | 14 | 2011-03-01 | 20 | 13 |  |  | 6 | 2011-03-03 | 20 | 13 | 2011-03-04 | 20 | 9 |  | 20 | 12 |  |  |  | 2011-03-07 | 20 | 6 | 2011-03-08 | 20 | 6 | 2011-03-09 |  | 5 | 2011-03-10 |  | 8 | Finished | [15 empty] | 140 | 92
[6 empty] | Meerut | 65 | 15 | 4 |  | 15 | Cancelled | [9 empty] | 2011-03-04 | 15 | 8 |  | 15 | 12 |  |  |  | 2011-03-07 | 15 | 5 | 2011-03-08 | 15 | 12 | 2011-03-09 |  | 11 | 2011-03-10 |  | 15 | 2011-03-11 |  | 15 | 2011-03-12 |  | 12 | [10 empty] | 75 | 90
[6 empty] | Saharanpur | 42 | 15 | 3 | 2011-02-28 | 15 | 13 | 2011-03-01 | 15 | 13 | 2011-03-02 | 15 | 11 | 2011-03-03 | 15 | 14 | 2011-03-04 | 15 | 7 | 2011-03-05 | 15 | 15 | [15 empty] | Finished | [15 empty] | 90 | 73
[6 empty] | Varanasi-1 | 92 | 20 | 5 | 2011-02-28 | 20 | 38 | 2011-03-01 | 20 | 36 | 2011-03-02 | 20 | 15 | 2011-03-03 | 20 | 14 | 2011-03-04 | 20 | 15 | 2011-03-05 | 20 | 16 |  |  |  | 2011-03-07 | 20 | 15 | 2011-03-08 | 20 | 22 | 2011-03-09 |  | 13 | 2011-03-10 |  | 15 | Finished |  |  | 2011-03-12 | [12 empty] | 160 | 199
[6 empty] | Varanasi-2 | 20 | 20 | 1 | [49 empty] | 0 | 0
| 9 | 9 | Uttarakhand | 114 | 2 | Haldwani | 64 | 15 | 4 | 2011-02-28 | 12 | 15 | 2011-03-01 | 12 | 15 | 2011-03-02 | 15 | 14 | 2011-03-03 | 15 | 12 | 2011-03-04 | 15 | 13 | 2011-03-05 | 15 | 15 |  |  |  | 2011-03-07 | 15 | 12 | 2011-03-08 | 15 | 15 | Finished | [21 empty] | 114 | 111
[6 empty] | Haridwar | 59 | 15 | 4 | 2011-02-28 | 15 | 11 | 2011-03-01 | 15 | 11 | 2011-03-02 | 15 | 12 | 2011-03-03 | 15 | 12 | 2011-03-04 | 15 | 11 | 2011-03-05 | 15 | 11 |  |  |  | 2011-03-07 | 15 | 14 | 2011-03-08 | 15 | 15 | Finished | [21 empty] | 120 | 97
South | 10 | 1 | Andaman & Nicobar (UT) | 19 | [29 empty] | 2011-03-08 | 11 | 9 | 2011-03-09 | 11 | 9 | 2011-03-10 | 8 | 9 | 2011-03-11 | 8 | 9 | [13 empty] | 38 | 36
| 11 | 2 | Andhra Pradesh | 1147 | 11 | Anantapur-1 | 174 | 25 | 6 | [12 empty] | 2011-03-04 | 26 | 26 | 2011-03-05 | 26 | 26 |  |  |  | 2011-03-07 | 26 | 26 | 2011-03-08 | 26 | 26 | [22 empty] | 104 | 104
[6 empty] | Anantapur-2 | [30 empty] | 2011-03-09 | 32 | 31 | 2011-03-10 | 32 | 31 | 2011-03-11 | 32 | 21 | 2011-03-12 | 32 | 21 | [10 empty] | 128 | 104
[6 empty] | Kurnool | [24 empty] | 2011-03-07 | 28 | 28 | 2011-03-08 | 28 | 28 | 2011-03-09 | 27 | 25 |  | 27 | 26 |  | - | - |  | - | - | [10 empty] | 110 | 107
[6 empty] | Guntur | 58 | 20 | 3 | [12 empty] | 2011-03-04 | 18 | 18 | 2011-03-05 | 18 | 18 |  |  |  | 2011-03-07 | 18 | 15 | 2011-03-08 | 18 | 14 | 2011-03-09 | 19 | 23 | 2011-03-10 | 19 | 24 | 2011-03-11 | - | - | 2011-03-12 | - | - | [10 empty] | 110 | 112
[6 empty] | Hyderabad-1 | 145 | 25 | 6 | 2011-02-28 |  | Cancelled | 2011-03-01 | [17 empty] | 2011-03-07 | 24 | 23 | 2011-03-08 | 24 | 24 | 2011-03-09 | 26 | 22 | 2011-03-10 |  | 0 | 2011-03-11 | 24 | 19 | 2011-03-12 | 24 | 19 |  |  |  | 2011-03-14 | 22 | 19 |  |  |  |  | 144 | 126
[6 empty] | Hyderabad-2 | [24 empty] | 2011-03-07 | 20 | 18 | 2011-03-08 | 20 | 19 | 2011-03-09 | 21 | 18 | 2011-03-10 | 21 | 18 | 2011-03-11 | 26 | 23 | 2011-03-12 | 26 | 22 | [10 empty] | 134 | 118
[6 empty] | Mahbubnagar | 66 | 20 | 3 | [21 empty] | 2011-03-07 |  | 0 | 2011-03-08 | 22 | 21 | 2011-03-09 | 22 | 21 | 2011-03-10 | 22 | 18 | 2011-03-11 | 22 | 18 | 2011-03-12 | 22 | 13 | [10 empty] | 110 | 91
[6 empty] | Nizamabad | 71 | 25 | 3 | 2011-02-28 |  | Cancelled | 2011-03-01 | [17 empty] | 2011-03-07 |  | 0 | 2011-03-08 | 23 | 21 | 2011-03-09 | 23 | 21 | 2011-03-10 | 24 | 24 | 2011-03-11 | 24 | 25 | 2011-03-12 | - | - |  |  |  | 2011-03-14 | 24 | 23 | 2011-03-15 | 24 | 26 |  | 142 | 140
[6 empty] | Kamareddy | 110 | 20 | 5 | 2011-02-28 |  | Cancelled | 2011-03-01 | [17 empty] | 2011-03-07 | 25 | 17 | 2011-03-08 | 25 | 18 | 2011-03-09 |  | 0 | 2011-03-10 |  | 0 | 2011-03-11 | 25 | 27 | 2011-03-12 | 25 | 27 |  |  |  | 2011-03-14 | 25 | 25 | 2011-03-15 | 25 | 28 |  | 150 | 142
[6 empty] | Ongole | 57 | 20 | 3 | [12 empty] | 2011-03-04 | 19 | 19 | 2011-03-05 | 19 | 19 |  |  |  | 2011-03-07 | 19 | 19 | 2011-03-08 | 19 | 19 | 2011-03-09 | 19 | 19 | 2011-03-10 | 19 | 19 | 2011-03-11 | - | - | 2011-03-12 | - | - | [10 empty] | 114 | 114
[6 empty] | Nellaur | 47 | 20 | 3 | [12 empty] | 2011-03-04 | 16 | 19 | 2011-03-05 | 16 | 18 |  |  |  | 2011-03-07 | 16 | 15 | 2011-03-08 | 16 | 16 | 2011-03-09 | 16 | 15 | 2011-03-10 | 16 | 17 | 2011-03-11 | - | - | 2011-03-12 | - | - | [10 empty] | 96 | 100
[6 empty] | Srikakulam | 76 | 20 | 3 | 2011-02-28 | 20 | 20 | 2011-03-01 | 20 | 21 | [6 empty] | 2011-03-04 | 18 | 15 | 2011-03-05 | 18 | 15 |  |  |  | 2011-03-07 | 18 | 18 | 2011-03-08 | 18 | 18 | 2011-03-09 | 17 | 16 | 2011-03-10 | 17 | 16 | 2011-03-11 | - | - | 2011-03-12 | - | - | [10 empty] | 146 | 139
[6 empty] | Tirupati | 67 | 12 | 5 | [9 empty] | 2011-03-03 | 13 | 11 | 2011-03-04 | 13 | 12 | 2011-03-05 | 12 | 9 | 2011-03-06 | 12 | 9 | 2011-03-07 | 13 | 15 | 2011-03-08 | 13 | 15 | 2011-03-09 | 13 | 15 | 2011-03-10 | 13 | 16 | 2011-03-11 | 14 | 13 | 2011-03-12 | 14 | 13 | [10 empty] | 130 | 128
[6 empty] | Vijayawada-1 | 148 | 20 | 5 | 2011-02-28 | 20 | 20 | 2011-03-01 | 20 | 20 | [6 empty] | 2011-03-04 | 20 | 20 | 2011-03-05 | 20 | 20 |  |  |  | 2011-03-07 | 20 | 18 | 2011-03-08 | 20 | 18 | 2011-03-09 | 21 | 16 | 2011-03-10 | 21 | 16 | 2011-03-11 | 17 | 16 | 2011-03-12 | 17 | 16 | [10 empty] | 196 | 180
[6 empty] | Eluru | 47 | 15 | 3 | [12 empty] | 2011-03-04 | 16 | 14 | 2011-03-05 | 16 | 14 |  |  |  | 2011-03-07 | 16 | 14 | 2011-03-08 | 16 | 14 | 2011-03-09 | 16 | 12 | 2011-03-10 | 16 | 13 | 2011-03-11 | - | - | 2011-03-12 | - | - | [10 empty] | 96 | 81
[6 empty] | Vizag-1 | 101 | 25 | 4 | 2011-02-28 | 26 | 26 | 2011-03-01 | 25 | 26 | [6 empty] | 2011-03-04 | 24 | 26 | 2011-03-05 | 24 | 26 |  |  |  | 2011-03-07 | 26 | 22 | 2011-03-08 | 26 | 22 | 2011-03-09 | 28 | 27 | 2011-03-10 | 28 | 27 | 2011-03-11 | - | - | 2011-03-12 | - | - | [10 empty] | 207 | 202
[6 empty] | Warangal | 51 | 25 | [28 empty] | 2011-03-09 | 26 | 28 | 2011-03-10 | 26 | 28 | 2011-03-11 | 25 | 21 | 2011-03-12 | 25 | 21 | [10 empty] | 102 | 98
| 12 | 3 | Goa | 19 | 1 |  | 17 |  | 2 | [6 empty] | 2011-03-02 | 10 | 10 | 2011-03-03 | 10 | 10 | 2011-03-04 | 9 | 9 | 2011-03-05 | 9 | 9 | [31 empty] | 38 | 38
| 13 | 4 | Karnataka | 236 | 4 | Bangalore | 74 | 15 | 5 | [12 empty] | 2011-03-04 | 13 | 15 | 2011-03-05 | 13 | 15 |  |  |  | 2011-03-07 | 12 | 15 | 2011-03-08 | 12 | 15 | 2011-03-09 | 11 | 15 | 2011-03-10 | 11 | 15 | 2011-03-11 | 15 | 11 | 2011-03-12 | 15 | 11 |  |  |  | 2011-03-14 | 13 | 16 | 2011-03-15 | 13 | 16 |  | 128 | 144
[6 empty] | Gulberga | 65 | 22 | 3 | [12 empty] | 2011-03-04 | 22 | 14 | 2011-03-05 | 22 | 14 |  |  |  | 2011-03-07 | 18 | 24 | 2011-03-08 | 18 | 25 | 2011-03-09 | 17 | 16 | 2011-03-10 | 17 | 16 | [16 empty] | 114 | 109
[6 empty] | Shimoga | 70 | 24 | 3 | [12 empty] | 2011-03-04 | 20 | 20 | 2011-03-05 | 20 | 20 |  |  |  | 2011-03-07 |  |  | 2011-03-08 |  |  | 2011-03-09 | 23 | 23 | 2011-03-10 | 23 | 23 | [16 empty] | 86 | 86
[6 empty] | Mangalore | 25 | 25 | 1 | [21 empty] | 2011-03-07 | 21 | 20 | 2011-03-08 | 21 | 20 | [22 empty] | 42 | 40
| 14 | 5 | Kerala | 185 | 5 | Kochi | 68 | 23 | 3 | [9 empty] | 2011-03-03 | 18 | 18 | 2011-03-04 | 18 | 18 | [6 empty] | 2011-03-07 | 19 | 19 | 2011-03-08 | 19 | 19 | 2011-03-09 | 17 | 16 | 2011-03-10 | 17 | 16 | [16 empty] | 108 | 106
[6 empty] | Trivandrum-1 | 21 | 21 | 1 | [9 empty] | 2011-03-03 | 19 | 19 | 2011-03-04 | 19 | 19 | [34 empty] | 38 | 38
[6 empty] | Trivandrum-2 | 32 | 21 | 2 | [9 empty] | 2011-03-03 | 18 | 18 | 2011-03-04 | 18 | 18 | [9 empty] | 2011-03-08 | 19 | 19 | 2011-03-09 | [21 empty] | 55 | 55
[6 empty] | Palakkad | 64 | 22 | 3 | [12 empty] | 2011-03-04 | 21 | 20 | 2011-03-05 | 21 | 20 |  |  |  | 2011-03-07 | 19 | 19 | 2011-03-08 | 19 | 19 | 2011-03-09 | 24 | 22 | 2011-03-10 | 24 | 17 | [16 empty] | 128 | 117
[6 empty] | Kannur | 22 | 22 | 1 | [9 empty] | 2011-03-03 | 22 | 20 | 2011-03-04 | 22 | 21 | [34 empty] | 44 | 41
| 15 | 6 | Lakshwadeep & Minicoy Island (UT) | 16 | [26 empty] | 2011-03-07 | 17 | 16 | 2011-03-08 | 17 | 10 | [22 empty] | 34 | 26
| 16 | 7 | Odissa | 378 | 7 | Balasore | 66 | 14 | 5 | 2011-02-28 | 13 | 13 | 2011-03-01 | 13 | 13 |  |  |  | 2011-03-03 | 13 | 9 | 2011-03-04 | 13 | 9 | [6 empty] | 2011-03-07 | 13 | 9 | 2011-03-08 | 13 | 9 | 2011-03-09 | 13 | 13 | 2011-03-10 | 13 | 12 | 2011-03-11 | 13 | 11 | 2011-03-12 | 13 | 11 | [10 empty] | 130 | 109
[6 empty] | Sambalpur | 59 | 12 | 5 | 2011-02-28 | 12 | 13 | 2011-03-01 | 12 | 13 |  |  |  | 2011-03-03 | 12 | 6 | 2011-03-04 | 12 | 6 | [6 empty] | 2011-03-07 | 12 | 7 | 2011-03-08 | 12 | 10 | 2011-03-09 | 12 | 9 | 2011-03-10 | 12 | 11 | 2011-03-11 | 12 | 13 | 2011-03-12 | 12 | 13 | [10 empty] | 120 | 101
[6 empty] | Rourkela | 26 | 13 | 2 | [9 empty] | 2011-03-03 | 13 | 10 | 2011-03-04 | 13 | 10 | [6 empty] | 2011-03-07 | 13 | 12 | 2011-03-08 | 13 | 13 | [22 empty] | 52 | 45
[6 empty] | Bhubaneshwar | 76 | 20 | 4 | [9 empty] | 2011-03-03 | 20 | 11 | 2011-03-04 | 20 | 23 | [6 empty] | 2011-03-07 | 20 | 15 | 2011-03-08 | 20 | 14 | 2011-03-09 | 20 | 19 | 2011-03-10 | 20 | 20 | 2011-03-11 | 16 | 18 | 2011-03-12 | 16 | 18 | [10 empty] | 152 | 138
[6 empty] | Cuttack | 30 | 10 | 3 | [9 empty] | 2011-03-03 | 10 | Cancelled | 2011-03-04 | 10 | Cancelled | [6 empty] | 2011-03-07 |  |  | 2011-03-08 |  |  | 2011-03-09 |  |  | 2011-03-10 | [18 empty] | 20 | 0
[6 empty] | Jeypore | 68 | 14 | 5 | 2011-02-28 | 12 | 8 | 2011-03-01 | 12 | 8 |  |  |  | 2011-03-03 | 12 | 9 | 2011-03-04 | 12 | 9 | [6 empty] | 2011-03-07 | 12 | 9 | 2011-03-08 | 12 | 7 | 2011-03-09 | 12 | 15 | 2011-03-10 | 12 | 15 | 2011-03-11 | 12 | 7 | 2011-03-12 | 12 | 7 | [10 empty] | 120 | 94
[6 empty] | Berhampur | 51 | 20 | 3 | [9 empty] | 2011-03-03 | 20 | 18 | 2011-03-04 | 20 | 18 | [6 empty] | 2011-03-07 | 20 | 7 | 2011-03-08 | 20 | 7 | 2011-03-09 | 20 | 27 | 2011-03-10 | 20 | 27 | [16 empty] | 120 | 104
| 17 | 8 | Puducherry (UT) | 33 | 1 | [11 empty] | 8 |  |  | 8 | 8 | 2011-03-04 | 8 | 8 | 2011-03-05 | 8 | 8 |  |  |  | 2011-03-07 | 9 | 8 | 2011-03-08 | 9 | 9 | 2011-03-09 | 8 | 8 | 2011-03-10 | 8 | 7 | [16 empty] | 66 | 56
| 18 | 9 | Tamil Nadu | 449 | 6 | Chennai | 49 | 25 | 2 | [6 empty] | 2011-03-02 | 20 | 18 | 2011-03-03 | 20 | 17 | 2011-03-04 | 15 | 18 | 2011-03-05 | 15 | 18 |  |  |  | 2011-03-07 | [27 empty] | 70 | 71
[6 empty] | Coimbatore | 73 | 25 | 3 | [6 empty] | 2011-03-02 | 23 | 23 | 2011-03-03 | 23 | 23 | 2011-03-04 | 26 | 25 | 2011-03-05 | 26 | 25 |  |  |  | 2011-03-07 | 24 | 25 | 2011-03-08 | 24 | 25 | [22 empty] | 146 | 146
[6 empty] | Madurai | 116 | 24 | 5 | [6 empty] | 2011-03-02 | 24 | 23 | 2011-03-03 | 24 | 23 | 2011-03-04 | 24 | 26 | 2011-03-05 | 24 | 27 |  |  |  | 2011-03-07 | 24 | 22 | 2011-03-08 | 24 | 22 | 2011-03-09 | 24 | 21 | 2011-03-10 | 24 | 21 | 2011-03-11 | 20 | 22 | 2011-03-12 | 20 | 22 | [10 empty] | 232 | 229
[6 empty] | Pondicherry | 68 | 20 | 4 | [6 empty] | 2011-03-02 | 14 | 22 | 2011-03-03 | 14 | 14 | 2011-03-04 | 14 | 14 | 2011-03-05 | 14 | 14 |  |  |  | 2011-03-07 | 12 | 12 | 2011-03-08 | 12 | 12 | 2011-03-09 | 12 | 12 | 2011-03-10 | 12 | 12 | [16 empty] | 104 | 112
[6 empty] | Trichy | 98 | 25 | 4 | [6 empty] | 2011-03-02 | 22 | 20 | 2011-03-03 | 22 | 20 | 2011-03-04 | 23 | 24 | 2011-03-05 | 23 | 24 |  |  |  | 2011-03-07 | 19 | 17 | 2011-03-08 | 19 | 17 | 2011-03-09 | 18 | 16 | 2011-03-10 | 18 | 16 | 2011-03-11 | 16 | 15 | 2011-03-12 | 16 | 19 | [10 empty] | 196 | 188
[6 empty] | Katpadi | 64 | 17 | 3 | [6 empty] | 2011-03-02 | 22 | 22 | 2011-03-03 | 22 | 22 | 2011-03-04 | 10 | 9 | 2011-03-05 | 10 | 10 |  |  |  | 2011-03-07 | 12 | 12 | 2011-03-08 | 12 | 12 | 2011-03-09 | 10 | 10 | 2011-03-10 | 10 | 10 | 2011-03-11 | 10 | 10 | 2011-03-12 | 10 | 10 | [10 empty] | 128 | 127
West | 19 | 1 | Chhatisgarh | 186 | 3 | Raipur | 97 | 30 | 3 | 2011-02-28 | 30 | 23 | 2011-03-01 | 30 | 23 |  |  |  | 2011-03-03 | 30 | 24 | 2011-03-04 | 30 | 27 | [6 empty] | 2011-03-07 | 32 | 19 | 2011-03-08 | 32 | 19 |  | No batch planned | No batch planned |  | No batch planned | No batch planned | [16 empty] | 184 | 135
[6 empty] | Bilaspur | 108 | 20 | 5 | 2011-02-28 | 20 | 40 | 2011-03-01 | 20 | 40 | 2011-03-02 | 20 | Postponed | 2011-03-03 | 20 | 17 | 2011-03-04 | 20 | 17 | [6 empty] | 2011-03-07 | 22 | 10 | 2011-03-08 | 22 | 9 | 2011-03-09 | 10 | 9 | 2011-03-10 | 10 | 11 | [16 empty] | 164 | 153
[6 empty] | Jagdalpur | 48 | 10 | 4 | 2011-02-28 | 10 | 7 | 2011-03-01 | 10 | 7 |  |  |  | 2011-03-03 | 10 | 14 | 2011-03-04 | 10 | 15 | [6 empty] | 2011-03-07 | Batch postponed to 9-10 March 2011 | Batch postponed to 9-10 March 2011 | 2011-03-08 | Batch postponed to 9-10 March 2011 | Batch postponed to 9-10 March 2011 | 2011-03-09 | 19 | 14 | 2011-03-10 | 19 | 14 | [16 empty] | 78 | 71
| 20 | 2 | Dadra Nagar & Heveli (UT) | 5 | [54 empty] | 0 | 0
| 21 | 3 | Daman & Diu (UT) | 8 | [54 empty] | 0 | 0
| 22 | 4 | Gujarat | 278 | 5 | Surat | 51 | 20 | 3 | 2011-02-28 | 20 | 4 | 2011-03-01 | 20 | 9 | 2011-03-02 | 20 | Postponed | 2011-03-03 | 20 | Postponed | 2011-03-04 | 20 | 5 | 2011-03-05 | 20 | 2 |  |  |  |  | Batch Postponed to 8th and 9th March 2011 | Batch Postponed to 8th and 9th March 2011 | 2011-03-08 | 15 | 20 |  | 15 | 6 |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 150 | 46
[6 empty] | Jamnagar | 65 | 12 | 5 | 2011-02-28 | 12 | 3 | 2011-03-01 | 12 | 2 | 2011-03-02 | 12 | 0 | 2011-03-03 | 12 | 0 | 2011-03-04 | 12 | 11 | 2011-03-05 | 12 | 12 |  |  |  | 2011-03-07 | 12 | 11 | 2011-03-08 | 12 | 11 | 2011-03-09 | 12 | 11 | 1900-01-10 | 12 | 11 | [16 empty] | 120 | 72
[6 empty] | Ahmedabad | 86 | 24 | 4 | 2011-02-28 | 24 | 24 | 2011-03-01 | 24 | 24 | 2011-03-02 | 24 | 18 | 2011-03-03 | 24 | 19 | 2011-03-04 | 24 | 15 | 2011-03-05 | 24 | 18 |  |  |  | 2011-03-07 | 17 | 6 | 2011-03-08 | 17 | 6 |  | 17 | 6 |  | 17 | 6 | [16 empty] | 212 | 142
[6 empty] | Anand | 50 | 12 | 4 | 2011-02-28 | 12 | 6 | 2011-03-01 | 12 | 7 | 2011-03-02 | 12 | 0 | 2011-03-03 | 12 | 0 | 2011-03-04 | 12 | 10 | 2011-03-05 | 12 | 10 |  |  |  | 2011-03-07 | 12 | 16 | 2011-03-08 | 12 | 18 |  | 8 | 4 |  | 8 | 4 | [16 empty] | 112 | 75
[6 empty] | Bhuj | 12 | 8 | 2 | 2011-02-28 | 8 | 6 | 2011-03-01 | 8 | 6 | 2011-03-02 | 8 | 3 | 2011-03-03 | 8 | 3 |  | NIL | NIL | [7 empty] | No Batch | No Batch |  | No Batch | No Batch |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 32 | 18
| 23 | 5 | Jharkhand | 257 | 3 | Dhanbad | 74 | 24 | 3 | [9 empty] | 2011-03-03 | 24 | 21 | 2011-03-04 | 24 | 20 | [6 empty] | 2011-03-07 | 25 | 11 | 2011-03-08 | 25 | 13 | 2011-03-09 | 24 | 16 | 2011-03-10 | 24 | 18 | [16 empty] | 146 | 99
[6 empty] | Hazaribagh | 41 | 20 | 2 | [9 empty] | 2011-03-03 | 20 | 16 | 2011-03-04 | 20 | 20 | [6 empty] | 2011-03-07 | 21 | 17 | 2011-03-08 | 21 | 20 |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 82 | 73
[6 empty] | Jamshedpur | 36 | 14 | 3 | [9 empty] | 2011-03-03 | 14 | 13 | 2011-03-04 | 14 | 13 | [6 empty] | 2011-03-07 | 12 | 8 | 2011-03-08 | 12 | 9 | 2011-03-09 | 12 | 9 | 2011-03-10 | 12 | 8 | [16 empty] | 76 | 60
[6 empty] | Ranchi-1 | 40 | 40 | 1 | [9 empty] | 2011-03-03 | 40 | 34 | 2011-03-04 | 40 | 39 | [7 empty] | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | [17 empty] | 80 | 73
[6 empty] | Ranchi-2 | 42 | 14 | 3 | [9 empty] | 2011-03-03 | 14 | 8 | 2011-03-04 | 14 | 9 | [6 empty] | 2011-03-07 | 14 | 2 | 2011-03-08 | 14 | 3 | 2011-03-09 | 14 | 4 | 2011-03-10 | 14 | 5 | [16 empty] | 84 | 31
| 24 | 6 | Madhya Pradesh | 417 | 6 | Gwalior | 37 | 20 | 2 | [6 empty] | 2011-03-02 | 20 | 14 | 2011-03-03 | 20 | 14 | 2011-03-04 | 20 | 10 | 2011-03-05 | 20 | 14 |  |  |  |  | 7 | 3 |  | No Batch | No Batch |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 87 | 55
[6 empty] | Bhopal | 84 | 30 | 3 | [6 empty] | 2011-03-02 | 30 | 14 | 2011-03-03 | 30 | 14 | 2011-03-04 | 30 | 11 | 2011-03-05 | 30 | 12 |  |  |  | 2011-03-07 | 30 | 15 | 2011-03-08 | 30 | 16 |  | 20 | 10 |  | 20 | 11 | 2011-03-11 | 20 | 7 | 2011-03-12 | 20 | 7 | [10 empty] | 260 | 117
[6 empty] | Indore | 34 | 34 | 2 | [6 empty] | 2011-03-02 | 34 | 11 | 2011-03-03 | 34 | 12 | 2011-03-04 | 34 | 11 | 2011-03-05 | 34 | 11 |  |  |  |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 136 | 45
[6 empty] | Dhar | 61 | 20 | 3 | [6 empty] | 2011-03-02 | 20 | 16 | 2011-03-03 | 20 | 15 | 2011-03-04 | 20 | 27 | 2011-03-05 | 20 | 28 |  |  |  | 2011-03-07 | 10 | 11 | 2011-03-08 | 10 | 14 |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 100 | 111
[6 empty] | Jabalpur | 75 | 20 | 4 | [6 empty] | 2011-03-02 | 20 | 0 | 2011-03-03 | 20 | 0 | 2011-03-04 | 20 | 19 | 2011-03-05 | 20 | 19 |  |  |  | 2011-03-07 | 20 | 12 | 2011-03-08 | 20 | 15 | 2011-03-09 | 20 | 9 | 2011-03-10 | 20 | 10 | 2011-03-11 | 20 | 13 | 2011-03-12 | 20 | 13 | [10 empty] | 200 | 110
[6 empty] | Satna | 74 | 20 | 4 | [6 empty] | 2011-03-02 | 20 | 20 | 2011-03-03 | 20 | 20 | 2011-03-04 | 20 | 17 | 2011-03-05 | 20 | 18 |  |  |  | 2011-03-07 | 20 | 14 | 2011-03-08 | 20 | 17 | 2011-03-09 | 19 | 14 | 2011-03-10 | 19 | 16 | [16 empty] | 158 | 136
| 25 | 7 | Maharashtra | 429 | 5 | Thane | 84 |  | 3 | 2011-02-28 | 30 | 7 | 2011-03-01 | 30 | 14 | 2011-03-02 | 30 | 15 | 2011-03-03 | 30 | 22 | 2011-03-04 | 30 | 14 | 2011-03-05 | 30 | 21 |  |  |  |  | No Batch | No Batch Scheduled |  | No Batch | No Batch |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 180 | 93
[6 empty] | Nagpur | 101 |  | 5 | 2011-02-28 | 20 | 11 | 2011-03-01 | 20 | 14 | 2011-03-02 | 20 | 4 | 2011-03-03 | 20 | 9 | 2011-03-04 | 20 | 15 | 2011-03-05 | 20 | 15 |  |  |  | 2011-03-07 | 20 | 3 | 2011-03-08 | 20 | 3 | 2011-03-09 | 20 | 14 | 2011-03-10 | 20 | 20 | [16 empty] | 200 | 108
[6 empty] | Kolhapur | 55 |  | 4 | 2011-02-28 | 15 | 16 | 2011-03-01 | 15 | 16 | 2011-03-02 | 15 | 10 | 2011-03-03 | 15 | 12 | 2011-03-04 | 15 | 10 | 2011-03-05 | 15 | 10 |  |  |  | 2011-03-07 | Batch Postponed to 8th and 9th March 2011 | Batch Postponed to 8th and 9th March 2011 | 2011-03-08 | 15 | 6 |  | 15 | 8 |  | No Batch Scheduled | [17 empty] | 120 | 88
[6 empty] | Aurangabad | 76 |  | 5 | 2011-02-28 | 15 | 11 | 2011-03-01 | 15 | 14 | 2011-03-02 | 15 | 4 | 2011-03-03 | 15 | 4 | 2011-03-04 | 15 | 17 | 2011-03-05 | 15 | 16 |  |  |  | 2011-03-07 | 15 | 12 | 2011-03-08 | 15 | 12 | 2011-03-09 | 15 | 12 | 2011-03-10 | 15 | 5 | Finished | [15 empty] | 150 | 107
[6 empty] | Solapur | 76 |  | 4 | 2011-02-28 | 20 | 17 | 2011-03-01 | 20 | 17 | 2011-03-02 | 20 | 15 | 2011-03-03 | 20 | 15 | 2011-03-04 | 20 | 18 | 2011-03-05 | 20 | 18 |  |  |  | 2011-03-07 | 20 | 14 | 2011-03-08 | 20 | 14 |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 160 | 128
| 26 | 8 | Rajasthan | 305 | 7 | Jaipur | 78 | 20 | 4 | 2011-02-28 | 20 | 21 | 2011-03-01 | 20 | 21 | 2011-03-02 | 20 | 19 | 2011-03-03 | 20 | 19 | 2011-03-04 | 20 | 17 | 2011-03-05 | 20 | 17 |  |  |  | 2011-03-07 | 16 | 15 | 2011-03-08 | 16 | 16 |  | No Batch Scheduled | No Batch Scheduled |  | No Batch Scheduled | No Batch Scheduled | [16 empty] | 152 | 145
[6 empty] | Ajmer | 48 | 24 | 2 | 2011-02-28 | 24 | 23 | 2011-03-01 | 24 | 23 | 2011-03-02 | 24 | 22 | 2011-03-03 | 24 | 22 | [10 empty] | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL | [16 empty] | 96 | 90
[6 empty] | Alwar | 23 | 12 | 2 | 2011-02-28 | 12 | 11 | 2011-03-01 | 12 | 11 | 2011-03-02 | 12 | 10 | 2011-03-03 | 12 | 12 | [10 empty] | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL | [16 empty] | 48 | 44
[6 empty] | Jodhpur-1 | 48 | 24 | 2 | 2011-02-28 | 24 | 21 | 2011-03-01 | 24 | 21 | 2011-03-02 | 24 | 22 | 2011-03-03 | 24 | 22 | [10 empty] | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL | [16 empty] | 96 | 86
[6 empty] | Jodhpur-2 | 25 | 16 | 2 | 2011-02-28 | 26 | 14 | 2011-03-01 | 26 | 14 | 2011-03-02 | 26 | 14 | 2011-03-03 | 26 | 14 | [10 empty] | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL | [16 empty] | 104 | 56
[6 empty] | Chhitorgarh | 40 | 20 | 2 | 2011-02-28 | 20 | 22 | 2011-03-01 | 20 | 22 | 2011-03-02 | 20 | 20 | 2011-03-03 | 20 | 20 | [10 empty] | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL | [16 empty] | 80 | 84
[6 empty] | Rajmasand | 8 | 12 | 1 | 2011-02-28 | 8 | 8 | 2011-03-01 | 8 | 8 | [16 empty] | NIL | NIL |  | NIL | NIL |  | NIL | NIL |  | NIL | NIL | [16 empty] | 16 | 16
East | 27 | 1 | Arunachal Pradesh | 128 | 1 | Itanagar | 126 | 16 | 4 | [27 empty] | 2011-03-09 | Starting from 10 March | Starting from 10 march | 2011-03-10 | 20 | 26 | 2011-03-11 |  |  | 2011-03-12 | 20 | 20 | 2011-03-13 | 20 | 20 | 2011-03-14 | 20 | 6 | 2011-03-15 | 20 | 7 |  | 100 | 79
| 28 | 2 | Assam | 272 | 2 | Jorhat-1 | 132 | 16 | 4 | [26 empty] | 8 | 2011-03-09 |  | 9 | 2011-03-10 |  | Strike | 2011-03-11 | 10 | 7 | 2011-03-12 | off | off |  |  |  | 2011-03-14 | 16 | 7 |  |  |  |  | 26 | 31
[6 empty] | Jorhat-2 |  | 16 | 4 | [24 empty] | 2011-03-08 | 16 | 8 | 2011-03-09 | 16 | 9 | 2011-03-10 |  |  | 2011-03-11 |  |  | 2011-03-12 | off | off | [10 empty] | 32 | 17
[6 empty] | Silchar | 39 | 20 | 2 | [24 empty] | 2011-03-08 | 20 | 16 | 2011-03-09 |  | 17 |  |  | 7 |  | 15 | 7 |  | off | off |  |  |  | 2011-03-14 | 20 | 6 |  |  |  |  | 55 | 53
[6 empty] | Dhemaji | 18 | 15 | 2 | [24 empty] | 2011-03-08 | 18 | 7 | 2011-03-09 |  | 7 | 2011-03-10 | 11 | 8 |  | 11 | 8 | Finished | Finished | Finished | [10 empty] | 40 | 30
[6 empty] | Nagaon | 33 | 20 | 2 | [24 empty] | 2011-03-08 | 20 | 11 | 2011-03-09 |  | 11 |  | 13 | 0 |  | 13 | 0 |  | off | off |  |  |  | 2011-03-14 | 20 | [5 empty] | 66 | 22
[6 empty] | Guwahati-1 | 88 | 30 | 4 | [9 empty] | 2011-03-03 | 20 | 6 | 2011-03-04 | 20 | 6 | 2011-03-05 | [8 empty] | 2011-03-08 | 30 | 16 | 2011-03-09 |  | 17 | 2011-03-10 |  | 7 | 2011-03-11 |  | 7 | 2011-03-12 |  | No training |  |  |  | 2011-03-14 | 30 | 13 |  |  |  |  | 100 | 72
[6 empty] | Guwahati-2 & Nagaland | [24 empty] | 2011-03-07 | 10 | 9 | 2011-03-08 | 20 | 22 | [22 empty] | 30 | 31
| 29 | 3 | Manipur | 31 | 1 | Imphal | 29 | 20 | 2 | [21 empty] | 2011-03-07 | 20 | 21 | 2011-03-08 | 20 | 23 | 2011-03-09 | 20 | 19 | Strike |  |  | Strike |  | Strike |  | Strike | Strike | [10 empty] | 60 | 63
| 30 | 4 | Meghalaya | 60 | 1 | Shillong | 46 | 15 | 3 | [21 empty] | 2011-03-07 | 15 | 12 | 2011-03-08 | 15 | 12 | 2011-03-09 | 15 | 12 | 2011-03-10 |  | 10 | 2011-03-11 |  | 7 | 2011-03-12 | off | off |  |  |  | 2011-03-14 | 15 | 12 |  |  |  |  | 60 | 65
| 31 | 5 | Mizoram | 46 | 1 | Aizawl | 44 | 22 | 2 | [24 empty] | 2011-03-08 | 22 | 16 | 2011-03-09 | 22 | 17 | 2011-03-10 | 15 | 7 | 2011-03-11 |  | 9 |  |  | 22 | [10 empty] | 59 | 71
| 32 | 6 | Nagaland | 59 | 1 | Guwahati | [52 empty] | 0 | 0
| 33 | 7 | Sikkim | 16 | 1 | Gangtok | 14 | 15 | 1 | [24 empty] | 2011-03-08 | 16 | 16 | 2011-03-09 | 16 | 16 | Finished | [18 empty] | 32 | 32
| 34 | 8 | Tripura | 52 | 1 | Agartala | 50 | 14 | 4 | [9 empty] | 2011-03-03 | 16 | 17 | 2011-03-04 | 16 | 17 | 2011-03-05 | [5 empty] | 2011-03-07 | 20 | 16 | 2011-03-08 | 20 | 16 | 2011-03-09 |  | 5 | 2011-03-10 | 17 | 5 | 2011-03-11 |  | 0 | 2011-03-12 |  | off | [10 empty] | 89 | 76
| 35 | 9 | West Bengal | 355 | 3 | Siliguri | 35 | 20 | 7 | [21 empty] | 2011-03-07 | 20 | 16 | 2011-03-08 | 20 | 13 |  | No Training | No training |  | No Training | No Training | [5 empty] | No training |  |  |  | 2011-03-14 | No Training |  | 2011-03-15 |  |  |  | 40 | 29
[6 empty] | Kolkata | 75 | 30 | 6 | [21 empty] | 2011-03-07 | 30 | 36 | 2011-03-08 | 30 | 35 | 2011-03-09 |  | 16 | 2011-03-10 |  | 10 | No training |  | No training | 2011-03-12 |  | No training |  |  |  | 2011-03-14 |  |  | 2011-03-15 |  |  |  | 60 | 97
[6 empty] | Malda | 38 | 20 | 2 | [21 empty] | 2011-03-07 | 20 | 14 | 2011-03-08 | 20 | 15 | 2011-03-09 |  | 17 | 2011-03-10 |  | 14 | Finished |  | Finished |  |  | No training |  |  |  | 2011-03-14 | No Training |  | 2011-03-15 |  |  |  | 40 | 60
[6 empty] | Rest of Bengal | 210 | [40 empty] | No training | [10 empty] | 0 | 0
Total |  |  |  | 7709 | 106 |  | 7606 | 2042 | 389 |  | 933 | 608 |  | 787 | 614 |  | 724 | 478 |  | 1520 | 1124 |  | 1640 | 1336 |  | 977 | 797 |  | 12 | 9 |  | 1480 | 1195 |  | 1745 | 1424 |  | 938 | 1133 |  | 836 | 952 |  | 485 | 542 |  | 399 | 467 |  | 20 | 28 |  | 220 | 146 |  | 82 | 77 | Total Training days | 12798 | 10930
[12 empty] | 65.17% |  |  | 78.02% |  |  | 66.02% |  |  | 73.95% |  |  | 81.46% |  |  | 81.58% |  |  | 75% |  |  | 80.74% |  |  | 81.6% |  |  | 120.8% |  |  | 113.9% |  |  | 111.8% |  |  | 117% |  |  | 140% |  |  | 66.36% |  |  | 0.93902 |  |  | 85.4%
[56 empty] | Approx. Participants Trained/under Training |  |  | 6399 | 5465
70.89%
Note on AQ45: NIIT: 2nd Day trainings postponed to 14th March due to Million March Program.
Note on AH47: NIIT: cancelled due to less quorum and postponed to 8th March
Note on AH48: NIIT: cancelled due to less quorum and postponed to 8th March
Note on AN49: NIIT: cancelled due to NADRS Dist. Officers meeting at Banswada and postponed to 14th March
Note on AQ49: NIIT: cancelled due to NADRS Dist. Officers meeting at Banswada and postponed to 14th March
Note on Y72: satya: 3 Extra candidates have come today
Note on AN74: Lab:
Note on AN75: Lab:
Note on Y77: 3 people absent in previous batch attended
Note on AB77: 3 people absent in previous batch attended
Note on AH78: 1 person absent in previous batch attended
Note on AK78: 1 person absent in previous batch attended
Note on Y79: 3 people additional from Madurai, without planned. Informed DIO.
Note on AB79: 3 people additional from Madurai, without planned. Informed DIO..And theni
Note on AT79: 2 people absent in previous batch attended
Note on AW79: 2 people absent in previous batch attended

## District_Summary
NIC - NADRS Training Plan (Updated on 08-Mar-2011)
Region | S. No. |  | State/UT | # of Employees | Training Location | # of Participants | Status/ Attendance | % Completion
North | 1 | 1 | Bihar | 614 | Muzaffarpur | 154 | 71.5 | 46.43%
[5 empty] | Patna-1 | 141 | 69.5 | 49.29%
[5 empty] | Patna-2 | 140 | 25.5 | 18.21%
[5 empty] | Bhagalpur | 177 | 84.5 | 47.74%
| 2 | 2 | Chandigarh(UT) | 3 | Ambala | 3 | 0 | 0%
| 3 | 3 | Delhi (UT) | 31 | Delhi | 31 | 31 | 100%
| 4 | 4 | Haryana | 159 | Ambala | 67 | 36 | 53.73%
[5 empty] | Gurgaon | 30 | 16.5 | 55%
[5 empty] | Hisar | 65 | 40 | 61.54%
| 5 |  | Himachal Pradesh | 75 | Dharamshala | 22 | 0 | 0%
|  | 5 |  |  | Solan | 15 | 0 | 0%
[5 empty] | Shimla | 38 | 0 | 0%
| 6 | 6 | Jammu & Kashmir | 176 | Jammu | 46 | 35 | 76.09%
[5 empty] | Srinagar-1 | 47 | 61.5 | 130.9%
[5 empty] | Srinagar-2 | 47 | 15 | 31.91%
[5 empty] | Udhampur | 23 | 16 | 69.57%
| 7 | 7 | Punjab | 185 | Amritsar | 57 | 45.5 | 79.82%
[5 empty] | Jalandhar | 52 | 47.5 | 91.35%
[5 empty] | Patiala | 72 | 71.5 | 99.31%
| 8 | 8 | Uttar Pradesh | 964 | Agra-1 | 77 | 75 | 97.4%
[5 empty] | Agra-2 | 15 | 0 | 0%
[5 empty] | Allahabad-1 | 50 | 44.5 | 89%
[5 empty] | Allahabad-2 | 45 | 13.5 | 30%
[5 empty] | Bareilly | 95 | 93 | 97.89%
[5 empty] | Deoria | 45 | 32 | 71.11%
[5 empty] | Gorakhpur | 102 | 72.5 | 71.08%
[5 empty] | Jhansi | 42 | 34 | 80.95%
[5 empty] | Kanpur | 101 | 56.5 | 55.94%
[5 empty] | Lucknow 1 | 92 | 78 | 84.78%
[5 empty] | Lucknow -2 | 80 | 46 | 57.5%
[5 empty] | Meerut | 65 | 45 | 69.23%
[5 empty] | Saharanpur | 42 | 36.5 | 86.9%
[5 empty] | Varanasi-1 | 92 | 99.5 | 108.2%
[5 empty] | Varanasi-2 | 20 | 0 | 0%
| 9 | 9 | Uttarakhand | 114 | Haldwani | 64 | 55.5 | 86.72%
[5 empty] | Haridwar | 59 | 48.5 | 82.2%
South | 10 | 1 | Andaman & Nicobar (UT) | 19 |  | 19 | 18 | 94.74%
| 11 | 2 | Andhra Pradesh | 1147 | Anantapur-1 | 174 | 52 | 29.89%
[5 empty] | Anantapur-2 |  | 52
[5 empty] | Kurnool |  | 53.5
[5 empty] | Guntur | 58 | 56 | 96.55%
[5 empty] | Hyderabad-1 | 145 | 63 | 43.45%
[5 empty] | Hyderabad-2 |  | 59
[5 empty] | Mahbubnagar | 66 | 45.5 | 68.94%
[5 empty] | Nizamabad | 71 | 70 | 98.59%
[5 empty] | Kamareddy | 110 | 71 | 64.55%
[5 empty] | Ongole | 57 | 57 | 100%
[5 empty] | Nellaur | 47 | 50 | 106.4%
[5 empty] | Srikakulam | 76 | 69.5 | 91.45%
[5 empty] | Tirupati | 67 | 64 | 95.52%
[5 empty] | Vijayawada-1 | 148 | 90 | 60.81%
[5 empty] | Eluru | 47 | 40.5 | 86.17%
[5 empty] | Vizag-1 | 101 | 101 | 100%
[5 empty] | Warangal | 51 | 49 | 96.08%
| 12 | 3 | Goa | 19 |  | 17 | 19 | 111.8%
| 13 | 4 | Karnataka | 236 | Bangalore | 74 | 72 | 97.3%
[5 empty] | Gulberga | 65 | 54.5 | 83.85%
[5 empty] | Shimoga | 70 | 43 | 61.43%
[5 empty] | Mangalore | 25 | 20 | 80%
| 14 | 5 | Kerala | 185 | Kochi | 68 | 53 | 77.94%
[5 empty] | Trivandrum-1 | 21 | 19 | 90.48%
[5 empty] | Trivandrum-2 | 32 | 27.5 | 85.94%
[5 empty] | Palakkad | 64 | 58.5 | 91.41%
[5 empty] | Kannur | 22 | 20.5 | 93.18%
| 15 | 6 | Lakshwadeep & Minicoy Island (UT) | 16 |  | 16 | 13 | 81.25%
| 16 | 7 | Odissa | 378 | Balasore | 66 | 54.5 | 82.58%
[5 empty] | Sambalpur | 59 | 50.5 | 85.59%
[5 empty] | Rourkela | 26 | 22.5 | 86.54%
[5 empty] | Bhubaneshwar | 76 | 69 | 90.79%
[5 empty] | Cuttack | 30 | 0 | 0%
[5 empty] | Jeypore | 68 | 47 | 69.12%
[5 empty] | Berhampur | 51 | 52 | 102%
| 17 | 8 | Puducherry (UT) | 33 |  | 33 | 28 | 84.85%
| 18 | 9 | Tamil Nadu | 449 | Chennai | 49 | 35.5 | 72.45%
[5 empty] | Coimbatore | 73 | 73 | 100%
[5 empty] | Madurai | 116 | 114.5 | 98.71%
[5 empty] | Pondicherry | 68 | 56 | 82.35%
[5 empty] | Trichy | 98 | 94 | 95.92%
[5 empty] | Katpadi | 64 | 63.5 | 99.22%
West | 19 | 1 | Chhatisgarh | 186 | Raipur | 97 | 67.5 | 69.59%
[5 empty] | Bilaspur | 108 | 76.5 | 70.83%
[5 empty] | Jagdalpur | 48 | 35.5 | 73.96%
| 20 | 2 | Dadra Nagar & Heveli (UT) | 5 |  | 5 | 0 | 0%
| 21 | 3 | Daman & Diu (UT) | 8 |  | 8 | 0 | 0%
| 22 | 4 | Gujarat | 278 | Surat | 51 | 23 | 45.1%
[5 empty] | Jamnagar | 65 | 36 | 55.38%
[5 empty] | Ahmedabad | 86 | 71 | 82.56%
[5 empty] | Anand | 50 | 37.5 | 75%
[5 empty] | Bhuj | 12 | 9 | 75%
| 23 | 5 | Jharkhand | 257 | Dhanbad | 74 | 49.5 | 66.89%
[5 empty] | Hazaribagh | 41 | 36.5 | 89.02%
[5 empty] | Jamshedpur | 36 | 30 | 83.33%
[5 empty] | Ranchi-1 | 40 | 36.5 | 91.25%
[5 empty] | Ranchi-2 | 42 | 15.5 | 36.9%
| 24 | 6 | Madhya Pradesh | 417 | Gwalior | 37 | 27.5 | 74.32%
[5 empty] | Bhopal | 84 | 58.5 | 69.64%
[5 empty] | Indore | 34 | 22.5 | 66.18%
[5 empty] | Dhar | 61 | 55.5 | 90.98%
[5 empty] | Jabalpur | 75 | 55 | 73.33%
[5 empty] | Satna | 74 | 68 | 91.89%
| 25 | 7 | Maharashtra | 429 | Thane | 84 | 46.5 | 55.36%
[5 empty] | Nagpur | 101 | 54 | 53.47%
[5 empty] | Kolhapur | 55 | 44 | 80%
[5 empty] | Aurangabad | 76 | 53.5 | 70.39%
[5 empty] | Solapur | 76 | 64 | 84.21%
| 26 | 8 | Rajasthan | 305 | Jaipur | 78 | 72.5 | 92.95%
[5 empty] | Ajmer | 48 | 45 | 93.75%
[5 empty] | Alwar | 23 | 22 | 95.65%
[5 empty] | Jodhpur-1 | 48 | 43 | 89.58%
[5 empty] | Jodhpur-2 | 25 | 28 | 112%
[5 empty] | Chhitorgarh | 40 | 42 | 105%
[5 empty] | Rajmasand | 8 | 8 | 100%
East | 27 | 1 | Arunachal Pradesh | 128 | Itanagar | 63 | 39.5 | 62.7%
| 28 | 2 | Assam | 272 | Jorhat-1 | 66 | 15.5 | 23.48%
[5 empty] | Jorhat-2 | 66 | 8.5 | 12.88%
[5 empty] | Silchar |  | 26.5
[5 empty] | Dhemaji |  | 15
[5 empty] | Nagaon |  | 11
[5 empty] | Guwahati-1 | 88 | 36 | 40.91%
[5 empty] | Guwahati-2 & Nagaland | 16 | 15.5 | 96.88%
| 29 | 3 | Manipur | 31 |  | 29 | 31.5 | 108.6%
| 30 | 4 | Meghalaya | 60 | Shillong | 46 | 32.5 | 70.65%
| 31 | 5 | Mizoram | 46 | Aizwal | 44 | 35.5 | 80.68%
| 32 | 6 | Nagaland | 59 | Guwahati | 59 | 0 | 0%
| 33 | 7 | Sikkim | 16 | Gangtok | 16 | 16 | 100%
| 34 | 8 | Tripura | 52 | Agartala | 50 | 38 | 76%
| 35 | 9 | West Bengal | 355 | Siliguri | 35 | 14.5 | 41.43%
[5 empty] | Kolkata | 75 | 48.5 | 64.67%
[5 empty] | Malda | 38 | 30
[5 empty] | Rest of Bengal | 210 | 0 | 0%
Total |  |  |  | 7707 |  | 7592 | 5465
70.91%

## State_Summary
NIC - NADRS Training Plan (Updated on 10-Mar-2011)
Region | S. No. |  | State/UT | # of Trainees | Trained | Completion %
North | 1 | 1 | Bihar | 614 | 251 | 40.88% | 64.42%
| 2 | 2 | Chandigarh(UT) | 3 | 0 | 0%
| 3 | 3 | Delhi (UT) | 31 | 31 | 100%
| 4 | 4 | Haryana | 159 | 92.5 | 58.18%
| 5 | 5 | Himachal Pradesh | 77 | 0 | 0%
| 6 | 6 | Jammu & Kashmir | 176 | 127.5 | 72.44%
| 7 | 7 | Punjab | 185 | 164.5 | 88.92%
| 8 | 8 | Uttar Pradesh | 964 | 726 | 75.31%
| 9 | 9 | Uttarakhand | 114 | 104 | 91.23%
South | 10 | 1 | Andaman & Nicobar (UT) | 19 | 18 | 94.74% | 88.77% | 88.77%
| 11 | 2 | Andhra Pradesh | 1167 | 1043 | 89.37%
| 12 | 3 | Goa | 19 | 19 | 100%
| 13 | 4 | Karnataka | 236 | 189.5 | 80.3%
| 14 | 5 | Kerala | 185 | 178.5 | 96.49%
| 15 | 6 | Lakshwadeep & Minicoy Island (UT) | 16 | 13 | 81.25%
| 16 | 7 | Odissa | 378 | 295.5 | 78.17%
| 17 | 8 | Puducherry (UT) | 33 | 28 | 84.85%
| 18 | 9 | Tamil Nadu | 449 | 436.5 | 97.22%
West | 19 | 1 | Chhatisgarh | 186 | 179.5 | 96.51% | 70.74%
| 20 | 2 | Dadra Nagar & Heveli (UT) | 5 | 0 | 0%
| 21 | 3 | Daman & Diu (UT) | 8 | 0 | 0%
| 22 | 4 | Gujarat | 278 | 176.5 | 63.49%
| 23 | 5 | Jharkhand | 257 | 168 | 65.37%
| 24 | 6 | Madhya Pradesh | 417 | 287 | 68.82%
| 25 | 7 | Maharashtra | 429 | 262 | 61.07%
| 26 | 8 | Rajasthan | 305 | 260.5 | 85.41%
East | 27 | 1 | Arunachal Pradesh | 128 | 39.5 | 30.86% | 40.63%
| 28 | 2 | Assam | 272 | 128 | 47.06%
| 29 | 3 | Manipur | 31 | 31.5 | 101.6%
| 30 | 4 | Meghalaya | 60 | 32.5 | 54.17%
| 31 | 5 | Mizoram | 46 | 35.5 | 77.17%
| 32 | 6 | Nagaland | 59 | 0 | 0%
| 33 | 7 | Sikkim | 16 | 16 | 100%
| 34 | 8 | Tripura | 52 | 38 | 73.08%
| 35 | 9 | West Bengal | 355 | 93 | 26.2%
Total |  |  |  | 7729 | 5465 | 70.71%